| EVENT / ACTION | DATE | REMARKS | COMMENTS |
| --- | --- | --- | --- |
| AGREEMENT ON BALTIC FAB PP CONCEPT. | 05.11.2013 | BALTIC FAB PP Team Meeting | Or the „PP Working group” if later adopted by the Baltic FAB Board I propose a slight delay due to 24 OCT NCP WG meeting and the deadline 1 NOV for data related to ANS charges submission, as well as the holidays of the All Saints. |
| AGREEMENT ON THE PP TEMPLATE | 05-11-2013 | BALTIC FAB PP Team |  |
| ADOPTION BY THE EC OF UNION-WIDE PERFORMANCE TARGETS. | 31.12.2013 | 12 months before the beginning of the reference period |  |
| SETTING THE BALTIC FAB TARGETS FOR RP2 WITH ANNUAL VALUES CONSISTENT WITH THE UNION-WIDE PERFORMANCE TARGETS AND INCENTIVE SCHEMES. | 17.01.2014 | BALTIC FAB Board | Work in parallel on the national key performance indicators and performance indicators if applied |
| AN IDENTIFICATION OF EACH AIR NAVIGATION SERVICE PROVIDER CONCERNED AND ITS SPECIFIC CONTRIBUTION TO MEETING THE TARGETS | 17.01.2014 |  |  |
| ANSPS TO PROVIDE THE DRAFT BUSINESS PLANS WITH DESCRIPTION OF INVESTMENT, INCLUDING THAT NECESSARY TO ACHIEVE THE PERFORMANCE TARGETS, DETAILING THEIR RELEVANCE IN RELATION WITH THE EUROPEAN ATM MASTER PLAN, THE NETWORK STRATEGY PLAN AND THE COMMON PROJECTS | 25-02-2014 |  | NSA’s to evaluate the draft business plans of their ANSPs |
| DRAFT BUSINESS PLAN OF RESPECTIVE MET SERVICE PROVIDER | 05-03-2014 |  | Which service provider to be involved in service provision and in the Baltic FAB PP? |
| NSA’S OPINION ON THE DRAFT BUSINESS PLANS, IF NECESSARY, REQUEST FOR ADDITIONAL DATA, JUSTIFICATION IN THE BUSINESS PLANS. | 01-03-2014 |  |  |
| ANSPS TO PROVIDE FINAL BUSINESS PLANS WITH DESCRIPTION OF INVESTMENT, INCLUDING THAT NECESSARY TO ACHIEVE THE PERFORMANCE TARGETS, DETAILING THEIR RELEVANCE IN RELATION WITH THE EUROPEAN ATM MASTER PLAN, THE NETWORK STRATEGY PLAN AND THE COMMON PROJECTS | 15.03.2014 |  |  |
| ELABORATION AND SUBMISSION OF THE DRAFT BALTIC FAB PP FOR LITHUANIAN AND POLISH NSA’S FOR SIGNATURE APPROVAL. | 18.04.2014 |  | I suppose at this stage we can only approve, it shall be signed after the consultation with the stakeholders |
| DRAFT BALTIC FAB PP IS PROVIDED TO STAKEHOLDERS FOR CONSULTATION ON THE PERFORMANCE PLAN AND TARGETS | 25.04.2014 | 3 weeks before consultation meeting | We should take into consideration that PRB may coordinate consultations between all FABs and airspace users. |
| THE CONSULTATION MEETING | 16.05.2014 |  | Location: in BRUSSELS most PROBABLY. WE SHOULD FORESEE LOCAL CONSULTATION MEETINGS AS WELL |
| REVISION OF THE DRAFT BALTIC FAB PP IF NECESSARY |  |  |  |
| SUBMISSION OF THE BALTIC FAB PP COST EFFICIENCY ANNEXES FOR LITHUANIAN AND POLISH MOT FOR APPROVAL. | 02.06.2014 |  | The aggregated cost efficiency target is to be approved by the Baltic FAB Board Lithuanian and Polish ministries should approve the cost efficiency targets of their „national” PP’s. |
| LITHUANIAN AND POLISH MoTS APPROVAL OF BALTIC FAB PP COST EFFICIENCY SEPARATE ANNEXES. | 6.06.2014 |  | Lithuanian and Polish ministries should approve the cost efficiency targets of their „national” PP’s. |
| SUBMISSION OF THE BALTIC FAB PP FOR LITHUANIAN AND POLISH NSA SIGNATURE. | 9.06.2014 |  |  |
| BALTIC FAB BOARD APPROVAL FOR PERFORMANCE PLAN FOR RP2 | 28.06.2014 |  | It is in the interstate agreement that the Baltic FAB Board will approve, but approval should be made by the Member States (Article 13 of Reg. 390/2013) We should clarify this with the lawyers |
| SUBMISSION OF THE BALTIC FAB PP TO THE EUROPEAN COMMISSION | 30.06.2014 | 6 months before the beginning of the reference period |  |
| EC/ PRB ASSESSMENT OF THE BALTIC FAB PP | till 30.11.2014 | 5 months after submission |  |